## Φύλλο1
Date | Time | Task Description / Issues | Task Type | Condition
2024-05-19 | 12:00 - 15:00 | We read the assignment, discussed ways of implementation and tried to understand what it asks for. | Requirements Analysis | Completed
17:00 - 20:00
2024-05-20 | 18:00 - 21:30 | Having finished the analysis of the application requirements, we moved on to distribution of tasks. | Task distibution | Completed
2024-05-21 | 11:00 - 14:00 | Starting the development of the website by the Front-End Developer of the team. Construction of forms in html. | Development | Completed
15:30 - 18:00
21:00 - 23:00
2024-05-22 | 11:00 - 14:30 | Continued development of the website. | Development / Dev Ops Processes | Completed
Start website host process. Create a project in cloudflare that loads the site from the GitHub repository. Configuring the site to redeploy itself every time a GitHub addition is made.
17:00 - 23:00
2024-05-23 | 11:00 - 13:30 | Continued development of the website. | Development / Dev Ops Processes | Completed
Start creating Cloudflare Worker to communicate the Cloudflare D1 database with the website.
17:00 - 23:30
First successful deployment of the website on the web.
2024-05-24 | 16:00 - 21:00 | Continued development of the website. | Development / Dev Ops Processes Debugging | Under investigation
| 12:00 - 20:00 | Since the database was not sending the results in the expected way, and the time was quite limited, we decided to use the browser's localstorage as storage space.
|  | Start of documentation development. | Documentation Editing | Completed
2024-05-25 | 11:00 - 15:00 | Final fixes to the website. Last improvements and solving minor problems during the login and registration of the user. | Development / Bug fixing | Completed
17:00 - 20:00
|  | Continuation of the of documentation development. | Documentation Editing
2024-05-26 | 09:00 - 15:00 | Final inspection of the site and its functionality. Final inspection of the hosting service at CloudFlare and check for any additional configurations needed. Making a video of the operation of the website and explanation of the page. | Final inspection / Presentation / Collection of files | Completed
Collection of files required for the delivery of the assignment.